Project Planning Phase
Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)
Date
18 October 2022
Team ID
PNT2022TMID41179
Project Name
Crude Oil Price Prediction
Maximum Marks
8 Marks
Product Backlog, Sprint Schedule, and Estimation (4 Marks)
Use the below template to create product backlog and sprint schedule
Functional
User
Sprint
User Story / Task
Story Points
Priority
Team Members
Requirement
Story
(Epic)
Number
As
a
user,
I
can
register
for
the
Registration
Sprint-1
USN-1
10
High
Soodappan K
application
by
entering
my
email,
password, and confirming
my password.
As a user, I will receive confirmation email
Sprint-1
USN-2
10
High
Sathish M
once I have registered for the application
As a user, I can log into the
Sprint-1
USN-3
15
High
Login
Sathish Kumar R
application by entering email &
password.
As a user, I can give Input Details to
Sprint-2
USN-4
15
High
Vijaysankar G
Data Collection
Predict Likeliness of crude oil
Transform raw data into suitable
Sprint-2
USN-5
15
High
Soodappan K
Data Pre-processing
format for prediction.
Sprint-3
USN-6
20
High
As a user, I can predict Crude oil using
Importing Liberaries
Sathish M
machine learning model.
Prediction of
Crude Oil Price
Sprint-3
USN-7
5
Medium
As a user, I can get accurate prediction of
Sathish Kumar R
crude oil
Sprint-4
USN-8
20
High
As a user, I can give feedback of the
Review
Vijaysankar G
application.

---
Project Tracker, Velocity & Burndown Chart: (4 Marks)
Sprint
Duration
Sprint Start Date
Story Points
Total Story
Sprint End Date
Sprint Release Date
Completed (as on
Points
(Planned)
(Actual)
Planned End Date)
Sprint-1
20
6 Days
24 Oct 2022
29 Oct 2022
20
29 Oct 2022
Sprint-2
20
6 Days
31 Oct 2022
05 Nov 2022
20
05 Nov 2022
Sprint-3
20
6 Days
07 Nov 2022
12 Nov 2022
20
 12 Nov 2022
Sprint-4
20
6 Days
14 Nov 2022
19 Nov 2022
 20
 19 Nov 2022
Velocity:
Imagine we have a 10-day sprint duration, and the velocity of the team is 20 (points per sprint). Let’s calculate the team’s average velocity (AV) per
iteration unit (story points per day)